Timeline Template

| Quarter | Objective 1 | Objective 2 | Objective 3 | Objective 4 | Objective 5 |
| --- | --- | --- | --- | --- | --- |
| 2026 Q2 |  |  |  |  |  |
| 2026 Q3 |  |  |  |  |  |
| 2026 Q4 |  |  |  |  |  |
| 2027 Q1 |  |  |  |  |  |

Timeline Example: These are some examples. You may adapt this template, but please keep it organized by quarter and objectives.

| Quarter | Objective 1: Cultural Burn Workshop | Objective 2: Engage Tribal Youth in Cultural Burning | Objective 3: Write grants to support cultural burn workshop | Objective 4: | Objective 5: |
| --- | --- | --- | --- | --- | --- |
| 2025 Q2 April –June | Gather Partners for virtual planning meeting | Hire Youth Coordinator | Hire grant writer and work with Program Manager to develop a list of programs needing funding. |  |  |
| 2025 Q3 July- September | Gather partners on land to make a plan. | Work with local elders program, and schools to coordinate dates for youth workshops | Write grant and get feedback from local practitioners. |  |  |
| 2025 Q4 October-December | Cultural Burn workshop with approx. 50 attendees | Hire local children’s caretakers to develop support local parents at Cultural Burn Workshop Host first youth workshop at Cultural Burn Workshop | Submit first round of grants. |  |  |
| 2026 Q1 January-March | Debrief with partners and review participant feedback | Hold 2 additional workshops. | Grant interviews Develop a list of additional grants to apply to |  |  |