MINISTRY EVENT PLANNING FORM

Olive Branch Community Church

Rev. Eugene E. Pearson

Pastor

416 Olney Sandy Spring Road

Sandy Spring, MD 20860  PH: 240-389-1045 www.obc-church.org

Ministry Event Planning Form

7 P’s - 90 Day Rule

Prayer& Proper Prior Planning Prevents Poor Performance

# 120 Days – 4 Months Out

- Submit Event Planning Request prior to Steering Committee Meeting (1st Tuesday of month) admin@obc-church.org and jpreston@obcchurch.org

- Check availability on calendar, ensuring that there are no conflicts for that date

- add to agenda for next Steering Committee Meeting

# 90 Days – 3 Months Out

At Steering Committee Meeting

- Ministry Head will give overview of proposed event

- Receive input from committee regarding

- Receive approval from necessary Ministry Heads to move forward (based on the needs for the event)

- Provide need for promotional materials (i.e. flyers, website, Keeping you Informed)

- Provide an update on needs for the event (i.e.

speakers, food, set-up)

# 60 Days – 2 Months Out

- Advise Steering Committee of any changes

- Advise supporting ministries of any logistical plans (i.e., setup/breakdown, seating or table arrangements)

- Request assistance from Finance Committee regarding purchases or contracts

# 30 Days – 1 Month Out

- Confirm all payments have been made

- Confirm registration process is in place

- Work with Finance Committee to set up registration process

- Setup regularly scheduled meeting with Finance

Committee to check payments/donations received

- Ensure setup, breakdown and cleanup teams are in place

# 2 weeks out

- Hold pre-event meeting with necessary Ministry

Heads and Building and Grounds Manager/Sexton

- Confirm number of attendees and cut-off date for receiving donations

- Confirm with vendors that payment has been received

# 1 week out

- Re-confirm Ministry Teams are ready and provide any necessary updates

- Finalize registration details

- Inform Building & Grounds Manager of  any necessary changes/tweak

Ministry Event Planning Form

7 P’s - 90 Day Rule

Prayer & Proper Prior Planning Prevents Poor Performance

All Olive Branch Community Church (OBCC) Ministries should use this form to host an event/program at OBCC or an off-site location.  Complete and submit a copy of this form to jpreston@obc-church and admin@obc-church at least 4 months prior to the event.  Refer to the Ministry Event Planning Timeline and Checklist for detailed guidelines for planning all events/programs.

|  | MINISTRY INFORMATION |
| --- | --- |
| MINISTRY | MINISTRY DIRECTOR OR COORDINATOR |
| EMAIL ADDRESS | PHONE |
|  | EVENT INFORMATION |

EVENT NAME  	TIME

DATE

LOCATION

# GOAL/OBJECTIVE (How does this event/program support our mission and vision?)

GUEST INFORMATION

Provide the following informa?on and biography on the proposed guest speaker or presenter for review and approval by the Pastor prior to the event.  Please do not contact or enter an agreement with a speaker or presenter.  There is no guarantee your sugges?on will be approved, the Pastor will give the final approval.

# NAME

PHONE

EMAIL ADDRESS

# MAILING ADDRESS

ADDITIONAL GUEST(S)

NAME

PHONE

TYPE (i.e., Choir, Musician)  NAME

PHONE

TYPE (i.e., Choir, Musician)  NAME

# PHONE  TYPE (i.e., Choir, Musician)

SUPPORTING MINISTRY INFORMATION

In an effort to provide efficient communication regarding OBCC events/programs, explain the scope of the event/program needs from other Ministries.   Please contact the Ministry Head, and Coordinator to discuss details and confirm ministry support.

| MINISTRY | YES/NO TYPE OF SUPPORT REQUESTED |  |  |  |
| --- | --- | --- | --- | --- |
| MINISTERS |  |  |  |  |
| ELDERS |  |  |  |  |
| MEDIA/TECH |  |  |  |  |
| MUSIC |  |  |  |  |
| SECURITY/PARKING LOT |  |  |  |  |
| USHER |  |  |  |  |
| HOSPITALITY |  | OUTSIDE CATERER/VENDOR (Include contract) |  |  |
|  |  |  | CATERER INFORMATION |  |
|  |  |  | NAME |  |
|  |  |  | PHONE |  |
|  |  |  | EMAIL ADDRESS |  |
|  |  |  | MAILING ADDRESS |  |

ESTIMATED BUDGET

Is there an additional financial impact to OBCC for this event/program?  Yes  	 No

| PROJECTED NUMBER OF PARTICIPANTS |  |  |
| --- | --- | --- |
| EVENT INCOME |  |  |
| TICKET SALES $ (PER TICKET) | $ |  |
| DONATIONS | $ |  |
| TOTAL INCOME |  | $ |
| EXPENSES |  |  |
| AUDIO/VISUAL SERVICES | $ |  |
| EQUIPMENT RENTAL | $ |  |
| HOSPITALITY | $ |  |
| HONORARIUM (SPEAKERS) | $ |  |
| HONORARIUM (MUSICIANS) | $ |  |
| MARKETING/OUTREACH | $ |  |
| SUPPLIES/VENDORS | $ |  |
| VENUE | $ |  |
| OTHER (SPECIFY) | $ |  |
| TOTAL EXPENSES | $ | $ |
| NET |  | $ |

While planning the event, each ministry should ensure all expenses are covered and there is no expense to the church.  All requests to purchase and/or contract goods and services require three quotes and prior approval by the Finance Committee and Elder Board.

Purchases/contractual agreements made without proper approval will not be reimbursed or honored by Olive Branch Community Church.  The individual(s) responsible for the purchase or contract is solely responsible for payment of the contract.

POST MINISTRY EVENT EVALUATION

EVENT  	 	 	 	 	 DATE OF EVENT ______________________

# EVENT COORDINATOR   	 MINISTRY HEAD______________________

| Checklist Item | Yes | No | Rating | Comments |
| --- | --- | --- | --- | --- |
| Did the event start on time? |  |  | Poor Fair Excellent (circle one) |  |
| Did the event meet the desired/expected number of participants? |  |  | Poor Fair Excellent (circle one) |  |
| Did the event meet the mission and vision of the Church? |  |  | Poor Fair Excellent (circle one) |  |
| Did the Ministry use effective advertisement months before the evet? |  |  | Poor Fair Excellent (circle one) |  |
| What did you like the most or least about the event? |  |  | Poor Fair Excellent (circle one) |  |
| Did the event meet your expectations? |  |  | Poor Fair Excellent (circle one) |  |
| Overall rating and comments. |  |  | Poor Fair Excellent (circle one) |  |