## Slide 1
Pre-meeting preparation
Notes: Pre-meeting preparation:
Feel free to break this PowerPoint into multiple sessions and customize it to best fit the needs of your area.
Determine the best tool for recording notes for each discussion and activity. If you are meeting in-person, prepare a flipchart and markers. If you are meeting virtually, prepare your preferred note-taking tool and share your screen so all participants can follow along. Remember to distribute a copy of the notes with participants after the meeting.
Have notes available from previous meetings, for example, the working groups formed and their members, the results of the SWOT analysis, Parking Lot questions and answers to be reviewed.
Use this information to make the following adjustments to the PowerPoint:
  Using the information collected during Build A Vision- fill-in slides 6-9 by referencing your area’s SWOT analysis; and slides 10,21 and 34 with your area’s established membership goals.
  Slide 35 references the meeting for the next Global Membership Approach step: Build Success. Discuss with your district leaders when you might hold this meeting in the next few months.
  Slide 32 references funding your initiatives. You may wish to print a copy of the Grants Available document, located on the Global Membership Approach webpage under ‘Process’ for yourself or for all the participants.
Create a “Parking Lot” to note comments and questions that may not be directly related to the task at hand. Your group may provide ideas in this meeting that would be good for your area’s Global Membership Approach plan or other initiatives. Create a specific flipchart paper or dedicated Word document for this purpose. By recording comments and questions to be addressed later, you can help your group stay focused.
When you are asking for input, call on Lions and Club Officers first to help this initiative resonate at the club level. Past International Officers and district team members should wait for all other Lions to have input first.
Remind Lions that this is a safe space for sharing, however if some Lions are uncomfortable sharing, ask them to email or private message you their opinions and make sure to record this data when sharing the PPT/information recorded with the audience. Consider using the free demo of www.sli.do as an online polling tool.
For breakout sessions, use your best judgement on how much time to allocate to each activity based on the total meeting time available.
Some slides in this presentation include two script versions:
  Script for GAT Area Leader to prepare district leaders to lead a Build a Vision workshop
  Script for district leaders when leading a Build a Team workshop

## Slide 2
Global Membership Approach
Build a Plan
1
Notes: Presenter notes:
____________________________________________________________
Welcome to this meeting of the Global Membership Approach. My name is ___ and I am _____.
We’re here to today to build our Global Membership Approach plan.

## Slide 3
Agenda
2
District Review
Action Plan
Resources
Next Steps
Notes: Presenter notes:
____________________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
This is the agenda for a Build a Plan workshop you will lead when you are back in your district. Start with a review of the district analysis you completed together during the Build a Vision workshop.
Next, you will spend time on action planning, both a review of how to build an action plan as well as brainstorming actual steps to implement for your district’s action plans.
Then, you will make sure everyone knows about the resources available to help with each action planning step. Finally, you will plan out next steps.
Script for district leaders when leading a Build a Plan workshop:
Today we’ll begin with a review of our district analysis and goals that we developed during our last meeting — Build a Vision.
Next, we’ll begin creating an action plan for each goal, by incorporating some of the items discussed in the District SWOT analysis.
Before we close out our session today, we’ll talk about some of the resources we have available to help us execute our plan. We’ll end our session by discussing next steps.

## Slide 4
Global Membership Approach Process
3
Build
Success
Build a
Plan
Build a
Vision
Build a
Team
Notes: Presenter notes:
____________________________________________________________
We’re on the 3rd step, Build a Plan.
It’s time to build our plan for our district. With that plan we will move forward to building our success.

## Slide 5
aa
Our Journey of Service
4
Notes: Presenter notes:
For this introduction section, feel free to modify/regionalize the questions based on the size of your group and time allocated for the meeting. You may also choose to do a knowledge check based on the information presented in the LLC courses on Goal Setting, Action Planning to Achieve District Goals, and Succession Planning. Alternatively, or discuss what type of feedback was received from the Lions outside of the working group on the District SWOT analysis.
____________________________________________________________
Let’s remember, growing membership is the primary goal of the Global Membership Approach. However, we cannot lose sight of why we grow membership. More membership means more Lions who will join us on the service journey.
Let’s introduce ourselves by providing our name, our club and our favorite type of service.

## Slide 6
5
Leverage our strengths
Manage our weaknesses
Take advantage of opportunities
Minimize impact of threats
District Analysis Exercise
5
THREATS
1.
2.
3.
OPPORTUNITIES
1.
2.
3.
WEAKNESSES
1.
2.
3.
STRENGTHS
1.
2.
3.
Notes: Presenter notes:
____________________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
At the conclusion of the Build a Vision workshop, everyone was asked to share the details of the district analysis with all clubs in their district as a way to generate support for the vision and solicit feedback. Encourage participants to share that feedback during the review.
You must prepare the next several slides prior to your local Build a Plan workshop. You will include the strengths, weaknesses, opportunities and threats captured during the Build a Vision workshop. You should also reflect on how to make connections between the district analysis and the action plans your district teams will create. As noted in the next several slides, you should prepare several examples of how to account for the district analysis details in your action plans.
Script for district leaders when leading a Build a Plan workshop:
Now that you’ve reviewed the District SWOT Analysis with additional members and leaders in your area, let’s review the specific items that we included in our District SWOT Analysis exercise and discuss any feedback you received.
Later, we’re going to apply what we learned about our district’s Strengths, Weaknesses, Opportunities and Threats to our plan.

## Slide 7
District Analysis - Strengths
6
STRENGTHS
1.
2.
3.
WEAKNESSES
1.
2.
3.
THREATS
1.
2.
3.
OPPORTUNITIES
1.
2.
3.
Notes: Presenter notes:
See notes on Slide 0. Complete before presenting.
Prior to the meeting, review the strengths identified and have an example ready of how one or two of the strengths can apply to completing an action plan to achieve the area’s established membership goals.
_____________________________________________________
Does anyone have anything we would like to add? (pause)
Now let’s dive a bit deeper — which of these strengths can we leverage when building our plan? (allow for participants to respond. If participants are struggling with responding, present ideas prepared prior to the meeting)

## Slide 8
District Analysis - Weaknesses
7
STRENGTHS
1.
2.
3.
WEAKNESSES
1.
2.
3.
THREATS
1.
2.
3.
OPPORTUNITIES
1.
2.
3.
Notes: Presenter notes:
See notes on Slide 0. Complete before presenting.
Prior to the meeting, review the weaknesses identified and have an example ready of how one or two of the weaknesses must be incorporated when completing an action plan to achieve the area’s established membership goals.
_____________________________________________________
Here we have our identified weaknesses within our district’s control — any others? Are all of these items still relevant? (pause)
What key improvements can we build into our plan to ensure these weaknesses turn into strengths or are planned for accordingly?
(Allow for participants to respond. If participants are struggling with responding, present ideas prepared prior to the meeting)

## Slide 9
District Analysis - Opportunities
8
STRENGTHS
1.
2.
3.
WEAKNESSES
1.
2.
3.
THREATS
1.
2.
3.
OPPORTUNITIES
1.
2.
3.
Notes: Presenter notes:
See notes on Slide 0. Complete before presenting.
Prior to the meeting, review the opportunities identified and have an example ready of how one or two of the opportunities can be leveraged when completing an action plan to achieve the area’s established membership goals.
_____________________________________________________
Here we have our identified opportunities outside of our control — any others? (pause)
What opportunities can we take advantage of? How can we leverage these opportunities to increase membership growth by implementing these actions into our plan?
(Allow for participants to respond. If participants are struggling with responding, present ideas prepared prior to the meeting)

## Slide 10
District Analysis - Threats
9
STRENGTHS
1.
2.
3.
WEAKNESSES
1.
2.
3.
THREATS
1.
2.
3.
OPPORTUNITIES
1.
2.
3.
Notes: Presenter notes:
See notes on Slide 0. Complete before presenting.
Prior to the meeting, review the threats identified and have an example ready of how one or two of the threats can be turned into opportunities when completing an action plan to achieve the area’s established membership goals.
_____________________________________________________
Lastly, we have our identified threats — feel free to add to the list but how can we avoid these threats, lessen their impact or turn them into opportunities?
(Allow for participants to respond. If participants are struggling with responding, present ideas prepared prior to the meeting)

## Slide 11
10
By the end of the _____ FY, our district will charter ________ new clubs.
By the end of the _____ FY, our district will induct ________ new members.
By the end of the _____ FY, our district will lose no more than ________ members.
Membership Goals
Notes: Presenter notes:
See notes on Slide 0. Complete before presenting.
You may also want to have past years’ numbers for your district to help with any questions. You can find past years’ numbers in the 5 Year Trend report: http://www8.lionsclubs.org/reports/5YearTrendReport
_____________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
This is the moment to review and possibly revise the goals you established during the Build a Vision workshop. Revisiting this after participants have obtained feedback from clubs in the district helps to strengthen support of the goals and plans.
Script for district leaders when leading a Build a Plan workshop:
In the Build a Vision meeting, we also established these goals in order to fulfill our mission of service.
Any more thoughts about our goals? Are they still realistic?

## Slide 12
11
Have a bias toward action - let’s see something happen now. You can break that big plan into small steps and take the first step right away.
“
”
- Indira Gandhi
Notes: Presenter notes:
Allow time for audience to read the slide.
________________________________________________________________
What does this quote mean to you? (pause for response)
Our established goals will take a lot of planning, with a lot of steps along the way, but every step we take will bring us that much closer to success. Therefore, every step completed should be celebrated, regardless of how small the task.
Next, let’s take a moment to review all the elements of a strong action plan.

## Slide 13
Action Plan Template
Area of Focus |  |  |  |  |  | 
☐ Service Activities ☐ Membership Development |  | ☐ Leadership Development ☐ LCIF |  |  | ☐ Custom Goal | 
Goal Statement |  |  |  |  |  | 
Action Step | Responsible Party |  | Required Resources (team members, technology, funding, etc.) | Date to Begin | Date to Begin | Due Date
Assessment |  |  | Alterations |  |  | 
Indicate what specifically, the district intends to accomplish.
What objective is your goal statement referring to?
Indicate how your team will accomplish the goal. The action step should be specific and measurable. Include details such as, number of Lions, specific activities, communications, etc.
Indicate the individuals who will do the work to complete each action step.
Indicate key resources or funding needed to execute each action step.
Indicate when the planning will need to begin to accomplish each action step. Remember to build in time to follow up with the responsible party when selecting a due date.
To be completed throughout the year; based on the assessment, what modifications to the listed timeline/action steps need to occur to accomplish the goal statement listed above.
To be completed throughout the year; any actions/feedback received that might affect the overall timeline and actions needed to accomplish the goal statement listed above.
Notes: Presenter notes:
____________________________________________________________
Here you will find the primary resource that you will use to create an action plan for each of the membership goals established. To better understand this resource let’s dive into each section (click)
First, we have the Area of Focus section which provides the working group with clear direction on the overall objective your goal statement is referring to. District teams will have the opportunity to use the Action Plan Template to complete their District Goals, which is why you’ll find service activities, membership development, leadership development, LCIF and a custom goal option in this section. For the Global Membership Approach, all of our action plans will solely focus on Membership Development. (click)
Next, we have the goal statement where you will indicate what the district intends to accomplish. Remember to create goals that are specific, measurable, actionable, realistic and time-bound in order to track our progress effectively. (click)
Each goal will have a number of action steps, which indicate how your working group will accomplish the goals. Every step of the process, from setting up a meeting to conducting training sessions in preparation for an event, should be listed in order to celebrate small successes along the way. (click)
Each action step, should list who will be primarily responsible for overseeing the action taken, which ensures accountability and helps resolve any questions of who should be completing each task. (click)
Required resources indicate what items, funding or people will be needed to complete each task. (click)
Date to begin indicates when planning for the action will start, while the due date is when the task will be complete. Remember to add ample time for follow up, if needed.(click)
The Assessment portion and Alterations portions will not be completed when you initially create an action plan but should be completed throughout the year. In the assessment portion you will include any action/feedback received that might impact the overall timeline or actions needed to complete the listed goal. (click)
On the other hand, the alterations section is based on the assessment and what modifications to the plan are needed in order to achieve the goal.
We will run through a few examples of some action steps that can be used in a plan for each one of the focus areas shortly to help you better understand how to complete an action plan, but before we do, does anyone have any questions? (Pause)

## Slide 14
Sample Action Plans
13
Focus Area 1: New Clubs
Notes: Presenter notes:
____________________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
The next several slides will be an opportunity to first practice action planning by reviewing and discussing several sample goals and action plans. As we saw just now from the review of the template, action planning is a very detailed activity and each step is valuable for our success. Action planning becomes easier with practice.
The discussion also stimulates our thinking and creativity about potential action steps in each area of focus.
Script for district leaders when leading a Build a Plan workshop:
Great! Let’s move on to an example of a started action plan for focus area 1 - new clubs.

## Slide 15
Area of Focus |  |  |  |  |  | 
☐ Service Activities ☐ Membership Development |  | ☐ Leadership Development ☐ LCIF |  |  | ☐ Custom Goal | 
Goal Statement |  |  |  |  |  | 
By the end of December 202X, our district will charter 1 new Specialty Club. |  |  |  |  |  | 
Action Step | Responsible Party |  | Required Resources (team members, technology, funding, etc.) | Date to Begin | Date to Begin | Due Date
Create a club extension team | District GMT Coordinator |  | List of interested members, email | June 5, 202X |  | June 7, 202X
Select a location for the new club | Club Extension Team |  | Club and Community Needs Assessment, virtual meeting platform | June 10, 202X |  | June 20, 202X
Choose a theme for the new club based on the needs of the location selected. | Club Extension Team |  | Specialty Clubs website, virtual meeting platform | June 10, 202X |  | June 20, 202X
Promote new club on social media and other online platforms | Club Extension Team |  | Social Media post templates, New Club Event Communications, New Club Development Guide, Budget $100 online advertising | July 1, 202X |  | August 1, 202X
Assessment |  |  | Alterations |  |  | 
Notes: Presenter notes:
____________________________________________________________
As a reminder, this is just the start of an action plan- your completed action plan might be a lot longer.
For this example, we have the goal statement as “By the end of December, our district will charter 1 new specialty club.” When reviewing the action steps, what do you notice? (pause for the audience to review the example and provide a response)
Each action steps should begin (or contain for regional variations) an action verb. We are going to DO these things.
Remember to be specific when creating each action step because it will only help your working group track and monitor what has and has not been completed yet.
You’ll also notice that there can be a variety of other steps needed to complete this goal- this is only an example. What might need to occur before promoting a new club on social media? (pause for response) Maybe determining the process for how prospective members will be communicated with once they respond to the ad?
What other action steps will need to occur after promoting a new club on social media? What about determining where and how informational sessions will be held? Any other suggestions? (pause for response) Will there be any other promotion of the club? For instance, if our district wants to create a ‘Doctors and Nurses Specialty Club’ because of the large number of hospitals in the area, how will we work with hospital administration to promote the club to medical staff? Will we need to set-up a booth or have to have flyers printed that focus on our global causes that interest them?
This is a perfect example of how to incorporate our strengths, weaknesses, opportunities and threats as well. Going back to social media- our district’s social media presence could be very good or on the other hand, we might need help with creating social media posts because we are not as computer savvy. If social media is a strength, we can use it as our primary delivery method, while if it is a weakness, we might need to add an extra step to learn more of best practices of creating social media posts in order to convert this weakness into a strength.
The same goes for the example of creating a ‘Doctors and Nurses Specialty Club’. There might be an opportunity to form new clubs at local hospitals as they have not partnered with any other local organization yet, but a threat could include COVID-19, and the risk that we will not be able to meet with any of the hospital's administration directly so we might need to think through how else we can contact the hospital and communicate with them virtually.
The possibilities are endless and no idea on how to accomplish the goal is too big or too small as long as there are sufficient action steps to support it.

## Slide 16
Sample Action Plans
15
Focus Area 2: New Members
Notes: Presenter notes:
____________________________________________________________
Let’s review another example of a started action plan for focus area 2 — new members.

## Slide 17
Area of Focus |  |  |  |  |  | 
☐ Service Activities ☐ Membership Development |  | ☐ Leadership Development ☐ LCIF |  |  | ☐ Custom Goal | 
Goal Statement |  |  |  |  |  | 
By the end of August 202X, our district will equip all leaders with the tools they need to effectively recruit members. |  |  |  |  |  | 
Action Step | Responsible Party |  | Required Resources (team members, technology, funding, etc.) | Date to Begin | Date to Begin | Due Date
Schedule virtual meeting with Zone Chairpersons to review recruitment resources such as the Just Ask! Guide | District GLT Coordinator |  | Contact information of Zone Chairpersons, communications calendar, virtual meeting platform | May 1, 202X |  | May 15, 202X
Review recruitment resources with Zone Chairpersons and communicate request to train club leadership on resources | District GLT Coordinator |  | Just Ask! Guide to New Member Recruitment, virtual meeting platform | May 15, 202X |  | June 15, 202X
Begin club Leadership training on recruitment resources and best practices | Zone Chairpersons |  | Just Ask! Guide to New Member Recruitment, virtual meeting platform | June 15, 202X |  | August 15, 202X
Assessment |  |  | Alterations |  |  | 
Notes: Presenter notes:
____________________________________________________________
For this example, we have the goal statement as “By the end of August, our district will equip all leaders with the tools they need to effectively recruit members.” Let’s take a look at these action steps. (pause for the audience to review)
You’ll find that outside of containing action verbs, each action description is short, with a maximum of two sentences, being preferred. Even with short sentences, it’s important to provide specifics where possible.
What specifics are included in this example description? (pause for audience response. If not included in responses, discuss how the specific leader is assigned as the responsible party and how each required resource is listed.)
What other specifics would you include that aren’t listed above? (pause)

## Slide 18
Sample Action Plans
17
Focus Area 3: Member Satisfaction
Notes: Presenter notes:
____________________________________________________________
Moving forward, let’s take a look at another example of a started action plan for focus area 3 — member satisfaction.

## Slide 19
Area of Focus |  |  |  |  |  | 
☐ Service Activities ☐ Membership Development |  | ☐ Leadership Development ☐ LCIF |  |  | ☐ Custom Goal | 
Goal Statement |  |  |  |  |  | 
By the end of June 202X, our district will train clubs on how to build a customized member satisfaction plan. |  |  |  |  |  | 
Action Step | Responsible Party |  | Required Resources (team members, technology, funding, etc.) | Date to Begin | Date to Begin | Due Date
Review Member Satisfaction Guide and schedule meeting with Focus Area 3 members | Focus Area 3 Working Group Lead |  | Member Satisfaction Guide, contact information of focus area 3 members, email | January 15, 202X |  | January 25, 202X
Review Member Satisfaction Guide with Working Group members and discuss how clubs can modify it to best fit their needs. | Focus Area 3 Working Group Lead |  | Member Satisfaction Guide, virtual meeting platform | February 1, 202X |  | February 15, 202X
Schedule meetings with club leadership to review Member Satisfaction Guide and how it can be best applied. | Focus Area 3 Working Group Lead |  | Contact information of club leadership, MyLCI, virtual meeting platform, availability calendar | February 15, 202X |  | March 1, 202X
Assessment |  |  | Alterations |  |  | 
Notes: Presenter notes:
____________________________________________________________
For this example, we have the goal statement as “By the end of June, our district will train clubs on how to build a customized member satisfaction plan.” Let’s take a look at this action plan. (pause for the audience to review)
Specifically, let’s focus on the dates. Remember date ranges should include the prep work and follow up involved, not just when the action is implemented.
For action step 3, we have 2 weeks to schedule meetings with club leadership. Why do we think this much time should be allotted? (pause for the audience to respond. If not included in responses, discuss how the focus area working group members will have to pull the contact information of club leadership from MyLCI, contact each individual club leadership team, find a time that works best for everyone and schedule separate meeting on a virtual meeting platform, all while ensuring the working group members are available at those times).

## Slide 20
Sample Action Plans
19
Focus Area 4: Leader Support
Notes: Presenter notes:
____________________________________________________________
Lastly, let’s review an example of an action plan for Focus Area 4 — Leader Support.

## Slide 21
Area of Focus |  |  |  |  |  | 
☐ Service Activities ☐ Membership Development |  | ☐ Leadership Development ☐ LCIF |  |  | ☐ Custom Goal | 
Goal Statement |  |  |  |  |  | 
For the 202X-2X FY, our district will hold quarterly webinars to support club success, such as improving member engagement or social media use. |  |  |  |  |  | 
Action Step | Responsible Party |  | Required Resources (team members, technology, funding, etc.) | Date to Begin | Date to Begin | Due Date
Meet to discuss and choose first topic for October Club Success Webinar and define meeting logistics. Determine how to archive for future club use. | Focus area 4 Working Group |  | Virtual meeting platform | July 1, 202X |  | July 10, 202X
Collect supporting resources to be promoted during webinar | Focus Area 4 Working Group member- Lion Richard |  | Lionsclubs.org website, online resources | July 10, 202X |  | July 25, 202X
Request support of chosen webinar host | Focus Area 4 Working Group member- -Lion Jane |  | Contact information for webinar host, email | July 10, 202X |  | July 25, 202X
Assessment |  |  | Alterations |  |  | 
Notes: Presenter notes:
____________________________________________________________
For this example, we have the goal statement as “For the FY, our district will hold quarterly webinars to support club success, such as improving member engagement or social media use.” Let’s take a look at this action plan. (pause for the audience to review)
Does anyone have any questions about how we will document our actions? What’s missing here that we would want to add in our own action plans? (pause for response)

## Slide 22
Goal: #
Goal: #
Goal: #
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action Plan Summary
1 New clubs
2 New members
3 Member satisfaction
4 Leader support
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
21
Notes: Presenter notes:
See notes on Slide 0. Complete “Goal: #” before presenting.
_____________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
This slide summarizes the work to be achieved during the breakout sessions. It also helps everyone to see the big picture they are building for the district.
Script for district leaders when leading a Build a Plan workshop:
Here’s the structure of a Global Membership Approach plan. It’s organized by the four Global Membership Approach areas of focus: New Clubs, New Members, Member Satisfaction and Leader Support.
Under each area of focus we’ll choose what Action Steps we will take to meet our goal. Let’s begin with 2-3 actions. We can always reconvene and add more later. Remember- no idea is too big or too small so when discussing remember we can choose more complex action steps and work our way backwards or start small with detailed actions and work our way forward.
For example, an Action Step under Focus Area 1 could be to conduct a new club development workshop, which would be a more complex action step. While, for Focus Area 4 it could be to meet monthly with Zone Chairpersons to better understand club needs, which would be a more detailed action.
We will also provide a short description for each action and specify when we’ll do it, who will be responsible, and what resources and budget will support the action.
We will develop as many actions as we feel are valuable and achievable for each focus area.
Remember to incorporate our information recorded from the District SWOT Analysis.

## Slide 23
Strategic Planning
22
Support innovation
Ensure everyone contributes
Initial focus on quality of ideas
Be positive; no negative comments
Encourage wild ideas and challenge yourselves
Be creative
Combine and improve ideas
Notes: Presenter notes:
____________________________________________________________
We’re looking for innovative ideas to spark membership. So when any of us suggests an idea, all of us must be supportive.
We will break into groups to generate ideas for our actions. Make sure everyone in your group contributes at least 1 idea.
Each group needs a scribe, who will write down every idea. At this point you want many ideas to work with.
Be positive about every idea. Discuss an idea just enough so everyone understands it. Do not pass judgement, say it won’t work or it has been tried before. Be positive or be quiet. A wild-sounding idea could become a breakthrough. Applaud it.
Think about how your experience was when you started being a Lion. How can we recreate that feeling? What creative ideas were implemented when you began your service journey? How were you encouraged to move up the leadership ranks?
Once you have a list of ideas, pick out the ones with the most potential. Make sure everyone has input into which those are. Then, consider if they can be combined or improved.

## Slide 24
Identify Actions and Timing
1 New clubs
2 New members
3 Member satisfaction
4 Leader support
Organize into four groups: one for each area of focus
Each group creates a list of possible actions, then chooses the best 2-3 and adds descriptions and date ranges
A spokesperson from each group shares their ideas
As a group, we’ll finalize our list of actions
Notes: Presenter notes:
For breakout sessions, use your best judgement on how much time to allocate to each activity based on the total meeting time available.
_____________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
These are the instructions for the breakout sessions to begin drafting action plans.
(Review the instructions included on the slide and in the script below.)
Do you have any questions about this activity?
Do you anticipate any challenges when facilitating this activity in your district? Let’s anticipate challenges and identify some solutions together now.
(Allow time for discussion. Reflect on potential challenges and ways to address them, for example, dealing with disruptive or disengaged participants. Also encourage participants to share strategies with each other during the discussion.)
Script for district leaders when leading a Build a Plan workshop:
We will start identifying actions by breaking up into four groups, one for each focus area.
Each group will create a brainstorming list, welcoming creative thinking. From that list, they will choose the 2-3 most promising ideas and add descriptions and a date range, so we have an idea how long it will take to implement.
Then we’ll discuss and refine and even add to the ideas, so we end up with 2-3 of the highest priority actions for each area.
(Organize attendees into groups.)
Each group has 15 minutes to identify 2-3 actions and give them descriptions and date ranges.
Any questions before we start?
(When breakout sessions are complete, discuss the Action Steps for each area and ask for additions and changes. Document the results on slide 34, including a list of potential ideas to be considered after the highest priority actions are implemented. )

## Slide 25
Unless commitment is made,
there are only promises and
hopes; but no plans.
“
”
24
- Peter F. Drucker
Notes: Presenter notes:
____________________________________________________________
Is anyone familiar with Peter Drucker? {He was a famous business management consultant, educator and author.}
What does this mean to you? What does it mean to our plan?

## Slide 26: Sample Working Group Organization
: Working Group Lead
: Working Group Members
05
05
05
Focus Area 1:
New Clubs
Focus Area 2:
New Members
Focus Area 4:
Leader Support
Focus Area 3:
Member Satisfaction
Global Membership Approach Support Lead
Notes: Presenter notes:
Edit this slide to enter the names of your working group members already identified prior to the start of the meeting.
The chart itself can also be modified as needed to suit your district. It also does not need to be complete, as it will be re-examined during the Build Success step.
_____________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
This is the moment to review and possibly revise the Working Group structure you established during the Build a Team workshop. Revisiting this after-action planning is important to ensure that each task has the appropriate person assigned to it.
Script for district leaders when leading a Build a Plan workshop:
These are our Global membership Approach Working Group members. We have several Lion leaders already identified, but would anyone like to volunteer their name for any of the remaining areas or suggest another way we could organize ourselves to implement the actions we have identified?
Are there others we can ask to join us, for example Past District Governors or other Lion leaders in our district? (Pause for input)

## Slide 27
We’re on this journey together!
Support is available…
Global Action Team leaders
Lions Clubs International GAT Staff
PIPs, PIDs, PCCs and PDGs
Existing Committees
DGs in other districts
Zone/Region Chairpersons and Certified Guiding Lions
Club Leadership and Lion Members
GAT
CA Leader
Area Leader
MD Leaders
District Leaders
26
Notes: Presenter notes:
Feel free to make modifications to the leaders listed on this slide to best reflect regional adaptations
_____________________________________________________
At the beginning of this meeting, we talked about our Journey of Service. One of the great things about being a Lion is that help is always available to us. We just need to ask for it.
We have our Global Action Team with district, multiple district, area and constitutional area leaders.
We can call our LCI GAT staff, who can connect us with additional LCI resources.
We also have past international presidents, directors, council chairs and district governors with an abundance of valuable experience.
What about any existing committees already created like (input regional variations such as Young Lions Task Force)?
And we’re going through the same process as other districts, so we can share concerns and discuss solutions with other district governors.
What about our Zone/Region Chairpersons and Certified Guiding Lions. How can we utilize them to support our clubs and maximize our training?
Lastly, let’s not forget our club leadership and members because with their help and input we can impact change for many years to come.
Don’t forget we’re all on this journey together and we are all accountable for ensuring we reach success!

## Slide 28
Resources Available
27
Rejuvenate Districts with New Clubs
Getting Started
New Club Development guide describes the steps for starting a new club
New Club Development online training course in the Lions Learning Center (LLC)
Better Communities, Changed Lives brochure
Lions Clubs Interactive Map to spot locations for new clubs
Join Together Program webpage for creating clubs with other community organizations
Guiding Lion Program webpage to prepare Lion leaders for club support
New Member Orientation webpage and video to provide a solid introduction for new members
Contact membership@lionsclubs.org to request new club kit materials
Types of Clubs
Traditional Lions Club webpage
Specialty Clubs webpage
Virtual Clubs webpage and webinar recording
Lioness Bridge Program webpage
Leo-Lions Club webpage
Campus Clubs webpage
Club Branch webpage
www.lionsclubs.org/start-a-new-club
Notes: Presenter notes:
____________________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
Review the resources catalogued on the next several slides in preparation for a similar review with the members of your district. Following this review, you will lead another breakout activity to identify leaders and resources for each action step. Be prepared to recommend resources for the action steps your working groups identify.
Script for district leaders when leading a Build a Plan workshop:
Let’s review some of the resources available to us.
For our first focus area, you may already be familiar with many of these resources, such as the New Club Development guide.
Would anyone like to mention a resource they have used or have an interest in using? (pause for response)
Can we use any of these in our first goal? (pause for response)

## Slide 29
Resources Available
28
Revitalize Clubs with New Members
Getting Started
Invite Members webpage, including the Just Ask! Guide and Membership Application
Mentoring Program webpage
The Benefits of Being a Lion
Just Ask! New Member Recruiting Guide
Membership Application Flyer
Recruitment Night PowerPoint
New Member Induction Ceremonies
New Member Orientation
Rebuilding and Reactivating Clubs
Potential Members
Young Adults webpage with recruitment tools
Recruiting Community Influencers ideas
New Voices Initiative webpage and I am a Lion brochure
Leo-Lion webpage
www.lionsclubs.org/en/resources-for-members/resource-center/club-membership-chairperson
Notes: Presenter notes:
____________________________________________________________
We also have a number of resources to help us revitalize clubs with new members.
Check out existing materials like the Just Ask guide and new materials, like the Membership Benefits flyer.
How can we apply these to focus area 2? (pause for response)

## Slide 30
Resources Available
29
Re-motivate Members with New Fellowships and Exciting Service
Service
Club Activity Calendar, Service Impact Stories and Global Causes poster
100 Service Ideas list and specific service project ideas for Childhood Cancer, Diabetes, Environment, Hunger and Vision
The Serving Safely webpage and webinar recording on Virtual Service Activities
Service Project Planners, step-by-step guides to help your club serve in new ways
Service Toolkit webpage, including the Community Needs Assessment, Partnerships Guide and Fundraising Guide
Lions Advocacy webpage
The lionsclubs.org/service-reporting webpage has all the information on why and how to report service activities
Fellowship
Improving Club Quality webpage with links to tools including the Club Quality Initiative and Your Club Your Way guides
Member Satisfaction guide
Art of Recognition handbook
Club Health Assessment reports and associated Action Strategies
Club Assessment checklist
Troubleshooting Guide for clubs and districts
Notes: Presenter notes:
____________________________________________________________
There are a lot of different aspects to member satisfaction. The service resources here can help ensure our members are engaged in meaningful service activities, but we also need to pay attention to the fellowship within a club.
Has anyone used any of the tools here or is interested in a particular one? (pause for response)
Would any of these apply to our third goal? What about (insert favorite resource)? (pause for response)

## Slide 31
Resources Available
30
Support District and Club Leaders
The Lions Learning Center (LLC) offers all Lions and Leos the opportunity to learn and sharpen their knowledge of Lions fundamentals and leadership skills through online interactive courses. (Accessing the LLC) (LLC FAQs)
Club Officer and Zone and Region Chairpersons webpage with links to eBooks and other materials for each title
Zone Chairperson Training Materials webpage
Regional Lions Leadership Institute materials webpage
Quick tips documents for Conflict Resolution, Listening and Communication, Meeting Management and Public Speaking
Achievement Certificate template for local learning events
Notes: Presenter notes:
____________________________________________________________
The fourth focus area is leader support. What actions are we planning that will take advantage of any of these resources? (pause for response)

## Slide 32
Marketing Resources Available
31
Lions Clubs International
LCI Fact Sheet and Our Story
Videos Available for download list
Brand Guidelines document
Logos and Emblems webpage
Publicity
Public Relations Guide webpage
Social Media Checklist, Post Examples and How to Share Events
Social Media post templates for Facebook and Twitter
Video Job Brief, Shot List and Script Sample
Photo/Video Release
Document Templates
Brochure – Tri-fold A4 | 8.5x11in
Business Card – Did You Know 90x50mm | 3.5x2in
Business Card – Visit Us 90x50mm | 3.5x2in
Business Card – Learn More 90x50mm | 3.5x2in
Business Card – Contact Me 90x50mm | 3.5x2in
Document – General A4 | 8.5x11in
Flyer – Event A4 | 8.5x11in
Flyer – General A4 | 8.5x11in
Flyer – Half-page A4 | 8.5x11in
Postcard – Miss You A5 | 4x6in
Postcard – Did You Know A5 | 4x6in
Postcard – Visit Us A5 | 4x6in
Postcard – Address A5 | 4x6in
Advertising
Club Event Ad 8x12cm
Club Event Ad with Photo 8x12cm
Join Us Ad 8x12cm | 24x13.5cm | 29x27cm
Join Us Ad with Photo 8x12cm | 24x13.5cm | 29x27cm
New Club Ad 8x12cm
New Club Ad with Photo 8x12cm
Photos of Lions in Action
Beach Cleanup
Childhood Cancer
Community Garden
Diabetes
Disaster Relief
Notes: Presenter notes:
____________________________________________________________
Communication will be the key to all of our initiatives, and we have a number of marketing resources at our fingertips. Are there any resources here that you think we can use in our initiatives? (pause for response)

## Slide 33
Membership Development Grant
Public Relations Grant
GAT Success Story Funding
Leadership development district, multiple district & institute grants
LCIF Matching, Disaster Preparedness, SightFirst, Lions Quest, Diabetes, Hunger, Childhood Cancer & Community Impact grants
Specialty Clubs program
LCI / LCIF Funding Sources
32
Notes: Presenter notes:
_____________________________________________________
Some of our initiatives cost money. When we are putting a price tag on our actions, we should keep in mind that funding is available from LCI and LCIF for many types of initiatives.
Can anyone identify one of our actions that would fit with one of these funding programs? (pause for response)

## Slide 34
Organize into four groups: one for each area of focus
Add leaders, resources and a budget for each action
A spokesperson from each group shares their ideas
As a group, we’ll finalize this draft of our plan
Identify Leaders and Resources
1 New clubs
2 New members
3 Member satisfaction
4 Leader support
Notes: Presenter notes:
For breakout sessions, use your best judgement on how much time to allocate to each activity based on the total meeting time available.
_____________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
These are the instructions for the breakout sessions to help identify leaders and resources when drafting action plans.
(Review the instructions included on the slide and in the script below.)
Do you have any questions about this activity?
Do you anticipate any challenges when facilitating this activity in your district? Let’s anticipate challenges and identify some solutions together now.
(Allow time for discussion. Reflect on potential challenges and ways to address them, for example, motivating additional members to step up to lead action steps. Also encourage participants to share strategies with each other during the discussion.)
Script for district leaders when leading a Build a Plan workshop:
We’ll divide again into the four areas and discuss leaders, resources and budgets for each Action.
{Organize attendees into the four groups, based on their interests.}
A few things to keep in mind:
When thinking about leaders, everyone needs to contribute and share the load.
When thinking about resources, you don’t need to be comprehensive, just list a few key items.
For the budget, estimate costs for each component and then total them.
Finally, we don’t have to figure out everything today. We’ll have a follow up meeting to fill in any blanks.
We’ll take 15 minutes again to draft leaders, budgets and resources for our Action plan. Any questions before we get started?
While the working groups are conducting the breakout session. Record the information from Slide 23 on the next slide.

## Slide 35
Goal: #
Goal: #
Goal: #
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action Plan Breakdown
1 New clubs
2 New members
3 Member satisfaction
4 Leader support
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
Action step
Description
Date range
Leader(s)
Resources
Budget
34
Notes: Presenter notes:
See notes on Slide 0. Complete “Goal: #” before presenting.
____________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
Use this slide to capture notes from each breakout group’s discussion.
Script for district leaders when leading a Build a Plan workshop:
Now that we have a set of actions, descriptions and dates, let’s talk about who will be responsible, and the resources and funds needed to support each action.
Which Working Group would like to start? (record all information presented on slide)

## Slide 36
aa
Meet with your Working Group Team to complete your action plan
Review the Sample Action Plan Booklet
Share our plan for feedback before submitting as a part of your district goals!
Global Membership Approach Seminar: Build Success
Next steps
35
Notes: Presenter notes:
____________________________________________________________
Script for GAT Area Leader to prepare district leaders to lead a Build a Plan workshop:
Conclude the session by sharing the following reminders and plans for the Build Success workshop.
Script for district leaders when leading a Build a Plan workshop:
Like planting a tree, we’ve begun drafted our district’s Global membership Approach plan. What happens next?
Take some time and elaborate on the action plan. Were there great ideas discussed that you would like to add? Meet with your district teams to ensure every step is planned out and thought through.
Need more help with creating an action plan- review the Sample Action Plan Booklet found on the District Goals page: https://www.lionsclubs.org/en/resources-for-members/resource-center/districtgoals under FVDG/DGE District Goals Resources.
Also, if you haven’t already, review the courses on Goal Setting, Action Planning to Achieve District Goals and Succession Planning on the Lions Learning Center.
Next, I’ll send our plan for review. We can make improvements and then we can receive improvement suggestions from our multiple district and GAT teams. It’s important to note that as a part of the District Goals, your district teams will be asked to submit action plans for their specific membership goals. We can use the goals and action plans we develop here as a part of the submission process!
Our next Global Membership Approach step is called Build Success. That’s where we’ll talk more about executing our plan.
That meeting will be in _______ {month} and we’ll share the meeting details as we get closer.
Are there any questions about what’s next?

## Slide 37
Feedback?
© 2020 Lions Clubs International
Update 8/2022 EN
36
Notes: Presenter notes:
____________________________________________________________
Thank you for participating today. All the work we have done will help Lions clubs grow in our district and eventually around the world.
Would anyone like to provide feedback on this process? How did this meeting work for you?
Thank you again for all your contributions to the Global Membership Approach and all you do for Lions clubs.