## Instructions
| Execution Success Map™ Use Instructions ©2025 All rights Reserved – Houseal Group LLC | Links to Project Categories
When to use this tool during the project lifecycle: |  | Strategic & Growth
a. | During project initiation when establishing the project scope with project sponsor and key stakeholders to establish success criteria and have clear expectations for project outcomes. | Operational Improvement
b. | At predetermined points in the project for an outcome review to assess or project likelihood of success using preestablished data collection or critieria validation information. | Technology & Systems
c. | At the end of the project to measure the success based on the pre-set targets and means of measurement. | Compliance & Regulatory
Infrastructure & Facilities
INSTRUCTIONS |  | Organizational & People
Customer-Facing (External Delivery)
Pre-Work (Purpose: to set the tone for the discussion regarding WHY the project is being proposed) |  | Marketing & Brand Projects
| Write a one-sentence problem/outcome hypothesis for the project (i.e. 'We're doing this ERP project to reduce order to cash by 20% to release $X cash.' This is the 'WHY' for the project. | Innovation & R&D Projects
| Capture baseline metric data, establish a target and date as well as define where the data will come from, and who will be responsible for the data. | Crisis & Risk Response Projects
Select the most appropriate project category from the ES Map and review ideas for potential measures to have something in mind to start the discussion.
30-60 minute meeting with Sponsor and Stakeholders
Introduce the concept of success criteria and their purpose along with the Execution Success Map. Explain the elements of the map (Activities -> Deliverables -> Leading indicators -> Lagging indicators)
Begin with the end - Lagging indicators. Agree on 1-3 final outcomes expected for the project. For each one, write 'metric, baseline, target, due date, owner, data source) Example: 'Order entry time from 8m -> 5m by Q4, Ops leader owns, source: ERP Logs
For each lagging indicator, define 2-3 leading indicators you'll see weeks/months earlier that will be predictive of final outcome success. Add threshholds, cadence, and owner. Example: > 80% users trained by week 6, measured weekly, Ops Lead is owner
List the 5-8 key deliverables and link each to the leading/lagging measures that they influence. If a deliverable doesn't influence a measure, challenge it.
Throughout Project Lifecycle
During project planning, add Go/No Go milestones associated with the intermediate measures. Example: User Acceptance Testing AND Task success rate > 95% (leading). During the project if one of the thresholds for a leading measure is missed, this should trigger an automatic escalation, or at a minimum be reported as 'yellow' (NOT green!)
Build a mini benefits realization plan that will live in your status report out dashboard. It should include: Measure, Baseline, Target, Current data, Forecast for EoQ, Owner, Confidence (RYG). Include a post-go-live monitoring period and schedule a hand-off to the business owner.
Ensure that Status reporting dashboard includes two elements: Delivery status (scope, schedule, cost, risks, etc. AND Value status (leading and lagging measures with arrows/trends + one-line insight)
During regular reviews, discuss the leading indicators/trends noting what has changed, review top 3 issues and decisions needed, and any scope creep issues or unnecessary scope elements that can be cut.
At the end of the project, verify data outcomes by SME outside of project, and hand off the BRP (Benefits Realization Plan) to the run-state owner (Example: Ops Leader) with a 90-day stabilization plan and KPI contol limits.
DO / DON'T
DO: pick few, high-signal measures; tie every deliverable to a measure; time-box the definition session, validate with finance/ops, etc.
DON'T: move goalposts mid-flight; report activity without value; choose vanity metrics; let 'green delivery' mask 'red outcomes.'

## Tool
Execution Success Map™ Success Criteria Tool by Project Category and Sub-Type ©2025 All rights Reserved – Houseal Group LLC
Project Category / Sub-Type | Key Questions to Ask | Intermediate (Leading) Measures | Final Outcome Measures (Lagging)
Strategic & Growth
New product / service development | - How will we measure customer adoption? | • Prototype tested with ≥20 customers | • $X revenue within 12 months
| - What revenue or margin targets define success? | • 75% positive pilot feedback | • ≥80% customer satisfaction at launch
| - What’s the timeline for breakeven? | • Distribution channels secured before launch | • Gross margin ≥Y% by Year 2
Market expansion / new industry entry | - How do we know we’ve truly “entered” the new market? | • First customer contracts signed | • Market share ≥X% in 2 years
| - What share or penetration target is meaningful? | • Pipeline ≥$Y in 6 months | • Revenue from new market ≥$X
| - What early indicators matter? | • Local partners/distributors onboarded | • Customer base growth ≥Z%
Mergers, acquisitions, integrations | - What synergy targets must be achieved? | • Integration milestones achieved on time | • $X synergy savings realized in 12 months
| - How will employee/customer experience be protected? | • 80% employees transitioned to new systems | • Voluntary attrition < Z%
| - What cultural markers show success? | • Customer churn tracked monthly | • Customer churn < 5% in first year
Operational Improvement
Process optimization (Lean, Six Sigma) | - What baseline are we improving? | • % of processes mapped & validated | • Cycle time reduced ≥20%
| - How much efficiency is enough? | • Defects reduced ≥10% in 60 days | • Defect rate <1%
| - How will employees feel the improvement? | • Kaizen events completed | • Employee satisfaction +10 points
Cost reduction initiatives | - Where will savings show up? | • Savings identified and validated by Finance | • $X annual savings realized
| - How do we validate savings? | • Productivity/FTE trend monitored | • Productivity per FTE improved ≥15%
| - Who owns sustaining them? | • Early spend reduced ≥X% | • No negative impact on customer KPIs
Supply chain & logistics | - What reliability/lead time target? | • Supplier OTIF (on-time in-full) ≥90% | • On-time delivery ≥95%
| - What’s the cost vs. service tradeoff? | • Lead time variance reduced | • Logistics costs reduced ≥10%
| - How do we know resilience improved? | • Inventory turns improved | • Supply chain resilience index improved
Technology & Systems
IT implementations (ERP, CRM, data) | - What outcomes should the system enable? | • % users trained/certified | • 90%+ adoption in 3 months
| - How will we measure adoption? | • UAT pass rate ≥90% | • Order entry time reduced 30%
| - What’s the “critical transaction” metric? | • Data migration validation ≥70% | • Zero high-severity incidents post go-live
Digital transformation / automation | - What efficiency or CX metric should improve? | • Manual tasks reduced ≥10% in 60 days | • 25% reduction in manual tasks
| - How will we prove ROI? | • Early CX satisfaction +5 points | • NPS increase +10
| - What’s our adoption tipping point? | • ROI model validated | • Payback period < 18 months
Cybersecurity / data protection | - What risk are we mitigating? | • % employees completing training | • Zero critical breaches in 12 months
| - How will we measure reduced vulnerability? | • Vulnerability scans show risk trending down | • Audit score improves from X → Y
| - What’s the acceptable incident level? | • Incident response drills passed | • 100% compliance with security protocols
Compliance & Regulatory
Certification & standards (ISO, FDA, HIPAA) | - What’s the deadline for certification? | • % SOPs updated | • Certification achieved by deadline
| - What’s the pass/fail criteria? | • Mock audit pass rate ≥90% | • Zero major nonconformances
| - How do we sustain compliance? | • Training completion 100% | • Compliance processes embedded in SOPs
Health, safety, environmental | - What metrics matter most? | • Near-miss reports trending down | • Recordable incident rate < industry avg
| - What does “safe/compliant” look like? | • % staff trained in HSE | • Zero environmental violations
| - What’s the monitoring mechanism? | • Monthly inspections passed | • 100% compliance training
Audit remediation / risk mitigation | - What gaps are we closing? | • % of findings remediated | • 100% findings closed by deadline
| - How do we know controls work? | • Control testing pass rate ≥90% | • Risk rating reduced High → Moderate
| - What’s the timeframe for risk reduction? | • Risk register updated monthly | • No repeat findings next audit
Infrastructure & Facilities
Construction / relocation / renovation | - What defines “on-time, on-budget”? | • Milestone inspections passed | • Facility operational by agreed date
| - How will readiness be validated? | • Safety incidents = zero | • <5% budget variance
| - What risks must be minimized? | • % schedule milestones on time | • No safety incidents
Equipment installations / upgrades | - What benchmarks should equipment hit? | • Factory Acceptance Test passed | • Equipment uptime ≥95%
| - How quickly should ramp-up occur? | • Ramp-up milestones achieved | • Ramp-up to full production in X weeks
| - What uptime target? | • Preventive maintenance plan in place | • OEE improved by Y%
Plant / production line expansions | - What new capacity must exist on Day 1? | • Construction/installation milestones on time | • Capacity increased by X units/month
| - How will ROI be measured? | • Test runs meet throughput targets | • Breakeven < 2 years
| - What’s breakeven point? | • Staff trained before go-live | • Scrap/rework < 2%
Organizational & People
Change management / restructuring | - What behaviors prove change? | • % leaders trained in new model | • 80% adoption of new model
| - How do we measure acceptance vs. resistance? | • Pulse survey trend improving | • Engagement +10 points
| - What early indicators? | • Blockers tracked/resolved | • Key talent retention ≥90%
Workforce training / leadership dev. | - What gap are we closing? | • % completion of training | • 85% demonstrate skill in assessment
| - How will we measure behavior change? | • Assessments ≥80% pass rate | • Leadership pipeline readiness +20%
| - How will business feel it? | • Coaching sessions held | • Productivity per FTE improved X%
HR systems / benefits rollouts | - What adoption or satisfaction proves success? | • % employees onboarded to new system | • ≥90% self-service usage
| - How will employees experience it? | • User feedback ≥4/5 satisfaction | • Employee satisfaction +15%
| - What error rate acceptable? | • Early error rates tracked | • Error rate <1%
Customer-Facing (External Delivery)
Product / system installations | - How will the client judge success? | • Installation milestones on schedule | • 100% systems functional Day 1
| - What “day one” performance matters? | • Acceptance tests passed | • On-time, on-budget ≥95%
| - What’s the service level target? | • Training completed for client staff | • Client acceptance sign-off
Solution implementation / integration | - What ROI or capability must client realize? | • % adoption tracked at 30/60/90 days | • Client achieves ≥X% cost savings/performance
| - How will adoption be measured? | • UAT acceptance ≥90% | • ≥80% adoption in 3 months
| - What service-level target? | • Support tickets resolved within SLA | • Zero critical incidents
Customer onboarding / adoption | - What usage or engagement signals prove adoption? | • % completing onboarding within 30 days | • ≥85% active use by Month 3
| - What timeline defines ramp-up? | • Time-to-first-value tracked | • Renewal rate ≥90%
| - What retention markers matter? | • Health score monitored | • 75% fully onboarded in 30 days
Consulting / managed services | - What outcome is client paying for? | • Deliverables accepted on time | • Client achieves targeted ROI/performance
| - How do we track value vs. promise? | • Interim client feedback ≥4/5 | • 90%+ CSAT
| - What satisfaction threshold proves success? | • Value realization report issued | • Renewal/expansion secured
Customer success initiatives | - What outcome signals drive renewal? | • Usage metrics trending upward | • Renewal rate ≥95%
| - How do we know customers achieve value? | • Quarterly business reviews held | • Customer-reported value ≥X%
| - What’s the loyalty indicator? | • Early renewals secured | • NPS +10
Marketing & Brand Projects
Campaigns | - What behaviors do we want to change? | • Impressions/CTR ↑ | • Revenue uplift $X
|  | • Pipeline generated | • Market share gain
• Awareness ↑
Rebranding | - How do we know the brand resonates? | • Internal adoption of assets | • Recognition ↑
|  | • Customer feedback | • Positive coverage
• Acquisition growth
Customer experience | - What aspects of CX must improve? | • NPS tracked monthly | • Retention ≥95%
|  | • Complaint resolution faster | • LTV increased
• Advocacy ↑
Innovation & R&D Projects
Research initiatives | - What hypothesis are we testing? | • % experiments completed | • Viability confirmed
|  | • Peer reviews passed | • Knowledge documented
|  | • Early feasibility signals | • Decision to scale/exit
Prototype / PoC | - What functionality must be proven? | • Prototype built/tested | • Validated for market
|  | • ≥X test users | • Business case approved
|  | • ≥70% positive feedback | • Roadmap updated
Intellectual property | - What innovation requires protection? | • Invention disclosures filed | • Patent/IP filed/granted
|  | • Legal review milestones met | • Licensing enabled
Crisis & Risk Response Projects
Disaster recovery | - What must be restored first? | • RTO milestones hit | • Continuity restored
|  | • Critical services restored | • No data loss
• Confidence restored
Cyber incident | - What risk are we containing? | • Systems isolated | • Breach remediated
|  | • Forensics milestones met | • Reporting requirements met
• Zero repeats 12 mos
Supply chain disruption | - What contingencies exist? | • Alternate suppliers secured | • ≥95% delivery maintained
|  | • Inventory verified | • Continuity restored
• Customer impact minimal
©2025 All rights Reserved – Houseal Group LLC