## Notes
Prepared: Grant Bradley
Reviewed: Sam Mackwell
Approved: 12/06/2022

## Risk Register
|  | Midland Rail Heritage Trust |  |  | updated 23.03.21
Press the… Alt + Enter keys together to start a new line within a cell
| Describe the Hazard, and potential harm and consequences | List the context/consequence | Using the "Risk rating matrix" select from the dropdown list the likelihood and consequence |  |  | List the Controls | Using the "Risk rating matrix" select from the dropdown list the likelihood and consequence |  |  | List proposed future controls
| DESCRIPTION | CONTEXT/CONSEQUENCE | LIKELIHOOD | CONSEQUENCE | INHERENT RISK | CONTROLS | LIKELIHOOD | CONSEQUENCE | RESIDUAL RISK | FUTURE CONTROLS PROPOSED
| Description of hazard | Consequence of hazard | Possible | Moderate | High | Control 1 Control 2 | Unlikely | Minor | Low | Future control 1
ID | DESCRIPTION | CONTEXT/CONSEQUENCE | LIKELIHOOD | CONSEQUENCE | INHERENT RISK | CONTROLS | LIKELIHOOD | CONSEQUENCE | RESIDUAL RISK | FUTURE CONTROLS PROPOSED
Natural Event
1 | Weather Event | Heavy rainfall, high winds, electrical storm or snow fall all present a danger to personnel and infrastructure at the site. | Possible | Moderate | High | 1. Use weather forecasts to understand weather conditions that could effect personnel or operations on site. 2. Personnel to wear suitable clothing for the weather conditions. 3. Personnel to seek shelter in buildings should the weather conditions suddenly change for the worst. Consider exiting the site to prevent personnel been stranded on site. 4. Drains to be maintained to ensure water can disperse quickly. 5. Outside operations to be suspended if the weather conditions make it unsafe to continue. 6. Ensure no loose items that could be blown by the wind are left unsecure. | Possible | Negligible | Low
2 | Earthquake | An earthquake presents potential danger of injury or death to personnel and damage to infrastructure. | Possible | Major | Very High | 1. Personnel to follow government guidelines during an earthquake - drop, take cover, hold on. 2. Personnel on site to meet at Assembly point after an earthquake so everyone is accounted for. 3. Rolling stock to be chocked and/or hand brakes applied to prevent rolling stock moving. 4. Heavy items to be stored at ground level. 5. Workshop equipment secured to the ground. 6. Inspections of buildings and track to occur before use or re-entry to buildings. | Possible | Moderate | High
Infrastructure
3 | Track work | Railway tracks and associated infrastructure no built or maintained could lead to possible rail vehicle incident that could cause injury or death to personnel or public and damage to infrastructure and vehicles. | Possible | Major | Very High | 1. All track work to be built to MRHT standards. 2. Annual inspections to be completed on all track work and associated infrastructure. 3. Track defects to reported immediately to Engineering Manager to prioritise and remedy. 4. Drains to be maintained to prevent water undermining track bed and causing track to subside. | Rare | Major | Medium
4 | Buildings | Buildings not maintained could present a danger to personnel working in them should they collapse, or have faulty fixtures or fittings. | Possible | Major | Very High | 1. Building to be inspected annually for defects. 2. Building defects to be reported to Engineering Manager to prioritise and remedy. 3. Rubbish to removed from site to reduce the fuel for any potential fire. | Rare | Major | Medium
5 | Fences and gates | Boundary fences and gates if not maintained could allow unauthorised access to public or live stock to enter or exit the property. Live Stock could present a danger to other users of the MRHT site or neighbouring KiwiRail property. | Possible | Moderate | High | 1. Fences and gates to be inspected when MRHT personnel are on site. 2. Any repairs to be immediately completed. | Rare | Moderate | Low
6 | Open water drain/creek on northern boundary | The open drain/creek presents a risk of drowning should personnel or members of the public fall into it. | Possible | Major | Very High | 1. MRHT personnel to be made aware of open drain/creek during induction as a new MRHT volunteer. 2. Visitors to the site to be made aware of open drain/creek when visiting the site. 3. The open drain/creek is to be temporality fenced during open days at the MRHT site. | Rare | Major | Medium | Permanent fencing to be considered along open drain/creek boundary.
Rail Operations
7 | Collision between rail vehicles | A collision between a rail vehicle and personnel, or another rail vehicle or road vehicle, machine or building could cause injury or death and damage to property. | Possible | Major | Very High | 1. Only authorise trained drivers to operate rail vehicles. 2. Only authorised trained personnel to be in control of shunting movements. 3.Personnel if not directly involved and members of the public to be kept away from rail vehicle movements. 4. Road vehicles to be kept clear of all tracks so they don't present a Collison potential during rail vehicle movements. 5. Track clearances to be maintained at all times between structures, machinery and temporary works. 6. Handbrakes and or wheel chocks to be used to secure stationary rail vehicles. | Rare | Major | Medium
8 | Uncontrolled rail vehicles | A failure to a rail vehicle where it cannot be controlled could cause harm or death to personnel or members of the public. | Possible | Major | Very High | 1. Locomotive to be check for correct operation before use. 2. Locomotive and other rolling stock to maintained as per MRHT maintenance requirements. 3. Only authorised personnel to be involved in driving and shunting of vehicles. 4. Personnel to follow MRHT shunting procedure. 5. No loose shunting (kicking) is allowed. 6. All defects to be reported immediately to Engineering Manager for prioritising and remedy. 7. Locomotives to be secured or made in operative when stored to prevent un authorised use. | Rare | Major | Medium
9 | Personnel on track | Personnel working on track could be hit by rail vehicle during movements causing injury or death. | Possible | Major | Very High | 1. Work plan in place for work operation setting out work process and responsibilities. 2. Rail vehicles to be moved at low speed. 3. Authorised shunter on the ground to pilot rail vehicle into work site. | Rare | Major | Medium
10 | Visitors and members of the public on site | Visitors or members of the public on site may not be aware of rail vehicle movements and could be injured or die from been struck by rail vehicle. | Possible | Major | Very High | 1. All visitors or members of the public on site to be made aware of any rail vehicle movements. 2. Rail vehicle movements to be overseen by on the ground shunter who can also watch out for the visitors or members of the public. 3. Children to be supervised at all times while on site by care givers. 4. Boundary fencing in place and maintained. | Rare | Major | Medium
11 |  |  | Unlikely | Major | High |  | Rare | Major | Medium
Personnel or visitors injured while on site
12 | Slips or trips | Personnel or visitors could slip or trip and injure themselves while on site. | Possible | Moderate | High | 1. Personnel and visitors to avoid walking on rail tracks and ballast. 2. While walking on site follow clear areas staying away from vegetation or stored objects. 3. Site to have designated areas for material lay down and storing of equipment. 4. Personnel working on or using rolling stock to use handrails and steps to enter and exit. 5. Oil spills to be cleaned up immediately. 6. Personnel to wear correct footwear on site. | Rare | Moderate | Low
13 | Fall from elevated surfaces | When working on rolling stock or structures personnel could injure themselves if they fall. | Possible | Major | Very High | 1. Follow correct work practises. 2. Use handrails and guards to prevent falls. 3. Work platforms to be used if working at height on structures. | Rare | Major | Medium
14 | Exposure to cleaning fluids, oil, diesel and paint. | The exposer of personnel to cleaning fluids, oil, diesel and paint could cause injury to personnel. | Possible | Moderate | High | 1. Personnel to take care when using these products to reduce the risk of over exposure to them. 2. Safe handling procedures to be followed as set out by manufacture 3. Personnel to wear correct PPE for task such as gloves, full cover clothing, masks and safety glasses. | Rare | Moderate | Low
15 | Noise | Personnel exposed to prolonged or excessive noise could suffer hearing damage | Possible | Moderate | High | 1. Personnel to use ear muffs or ear plugs when using or close to noisy machinery. | Rare | Moderate | Low
16 | Eye damage | Personnel could suffer eye injury from machinery, air borne practicals, dust or tools during operation work on site. | Possible | Major | Very High | 1. Personnel to wear eye protection when working with work shop machinery, tools that create dust or create air borne practicals, working under rolling stock or using fluids that could be harmful to eyes. | Rare | Major | Medium
17 | Exposure to sun | Personnel could suffer sun burn, heat stroke or prolong effects for over exposure to the sun. | Possible | Moderate | High | 1. Personnel to wear appropriate clothing for their own risk level noting the next point. 2. The use of sun screen, sun hats, sun glasses and the wearing of shirts should be strongly encouraged if working outside for longer periods of time. | Rare | Moderate | Low
18 | Lifting | Personnel could be injured from lifting materials, equipment or machinery on site. | Possible | Moderate | High | 1. Personnel to follow correct lifting techniques. 2. Use two people for heavy items. 3. Use mechanical adds or machinery where possible to lift heavy items | Rare | Moderate | Low
19 |  |  | Unlikely | Moderate | Medium |  | Rare | Moderate | Low
Workshop machinery, tools, equipment, plant and mobile vehicles.
20 | Workshop Machine tools (Lathes, Drills etc.) | Rotating machinery, sharp tools and moving parts could injury personnel if not used correctly. | Possible | Moderate | High | 1. Authorised personnel only to use workshop machines. 2. Correct PPE to be worn by personnel. 3. Machines to be used correctly by personnel. | Rare | Moderate | Low
21 | Electric shock | Use of electrical tools and equipment could cause injury or death if correct procedures are not followed. | Possible | Major | Very High | 1. Authorised personnel only to use this equipment and tools. 2. Inspect equipment and leads before use and if any issues found don't use the item and report it. 3. Correct PPE to be worn by personnel. 4. Don't use electrical equipment in wet conditions. | Rare | Major | Medium
22 | Portable tools | Incorrect use of tools could cause injury to personnel. | Possible | Minor | Medium | 1. Authorised personnel only to use portable tools. 2. Correct PPE to be worn by personnel. 3. Don't use faulty tools. 4. Inspect tools before use, for any signs of damage. | Rare | Minor | Low
23 | Plant and equipment (Jacks, compressors, etc.) | Incorrect use could cause injury to personnel. | Possible | Moderate | High | 1. Authorised personnel only to use mobile plant. 2. Correct PPE to be worn by personnel. 3. Don't use faulty items. 4. Inspect plant and equipment before use, for any signs of damage. | Rare | Moderate | Low
24 | Mobile Plant (tractors, excavators etc.) | Incorrect use could cause injury to personnel. | Possible | Major | Very High | 1. Authorised personnel only to use plant and equipment. 2. Correct PPE to be worn by personnel. 3. Don't use faulty items. 4. Inspect mobile plant before use, for any signs of damage. 5. Repair and service mobile plant to keep it in good working order. | Rare | Major | Medium
25 |  |  | Likely | Moderate | Very High |  | Unlikely | Moderate | Medium
26 |  |  | Possible | Major | Very High |  | Unlikely | Major | High
|  |  | Likelihood | Consequence
|  |  | Rare | Negligible
|  |  | Unlikely | Minor
|  |  | Possible | Moderate
|  |  | Likely | Major
|  |  | Almost Certain | Catastrophic
[5 empty] | Negligible | Minor | Moderate | Major | Catastrophic
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6
|  |  |  | Rare | Low | Low | Low | Medium | High
|  |  |  | Unlikely | Low | Low | Medium | High | Very High
|  |  |  | Possible | Low | Medium | High | Very High | Very High
|  |  |  | Likely | Medium | High | Very High | Very High | Extreme
|  |  |  | Almost Certain | Medium | High | Very High | Extreme | Extreme

## Risk Matrix
|  |  |  | Rating | 1 | 2 | 3 | 4 | 5
|  |  |  | Media/ Reputation | Unnoticed by public & media | Limited or minor media comment | Local adverse media coverage | Short term adverse national media coverage | Sustained national or short term international media coverage
|  |  |  | Financial Damage | <$10,000 | $10,000 to $100,000 | $100,000 to $1 million | $1million to $10 million | >$10 million
|  |  |  | Safety | No medical treatment by professional medical personnel | Lost Time Injury | Possible fatality, severe injury | One fatality | More than one fatality and/or multiple severe injury
CONSEQUENCE
Rating | Frequency | Definition | LIKELIHOOD |  | Negligible | Minor | Moderate | Major | Catastrophic
1 | 40 Years | Unlikely to occur but possible. It can be assumed the hazard may exceptionally occur. |  | Rare | Low | Low | Low | Medium | High
2 | 20 Years | It can be reasonably expected for the hazard to occur |  | Unlikely | Low | Low | Medium | High | Very High
3 | 5 Years | Highly possible for the hazard to occur |  | Possible | Low | Medium | High | Very High | Very High
4 | 1 Year | (Almost certain) The hazard can be expected to occur frequently |  | Likely | Medium | High | Very High | Very High | Extreme
5 | 0.25 Year | Hazard is certain to occur or already has before |  | Almost Certain | Medium | High | Very High | Extreme | Extreme