## Repair Timeline
House Fire Solutions™ – Home Repair Timeline After a Fire (Month-by-Month Guide)
Month / Stage | Goal / Focus | Key Actions | Typical Duration | Common Delays / Risks | Status (🕒 / ⚠️ / ✅) | Notes
Week 1–2 | Immediate Aftermath | Secure property, contact insurer, document damage, arrange housing | 1–2 weeks | Adjuster delays | 🕒
Month 1 | Damage Assessment | Adjuster inspection, hire contractor, review coverage, start mitigation | 3–5 weeks | Claim approval delays | 🕒
Month 2 | Cleanup & Demolition | Remove debris, clean soot, dry out, inspect structure | 3–6 weeks | Permit/asbestos delays | 🕒
Month 3 | Structural Repairs | Rebuild framing, roofing, walls, insulation | 4–6 weeks | Material shortages | 🕒
Month 4 | Rough-In Work | Electrical, plumbing, HVAC rough-ins, inspections | 3–5 weeks | Failed inspections | 🕒
Month 5 | Interior Build-Out | Drywall, flooring, paint, carpentry, cabinets | 4–8 weeks | Custom orders | 🕒
Month 6 | Exterior Finishes | Siding, paint, gutters, windows, driveway | 3–6 weeks | Weather delays | 🕒
Month 7–8 | Finishing & Move-In Prep | Appliances, fixtures, cleaning, inspections | 4–6 weeks | Scheduling delays | 🕒
Month 9–10 | Final Inspections | City approval, insurance payout, warranties, move-in | 2–4 weeks | Inspection backlog | 🕒
Month 11–12 | Post-Rebuild | Submit receipts, maintenance, fire prevention upgrades | Ongoing | Paperwork backlog | 🕒

## Rebuild Checklist
House Fire Solutions™ – Rebuild Checklist by Category
Category | Key Task | Responsible Party | Due Date | Status (✅ / ⚠️ / 🕒) | Notes
Structural | Inspect foundation, rebuild framing and roof | Contractor |  | 🕒
Electrical | Rewire circuits, replace damaged outlets | Licensed Electrician |  | 🕒
Plumbing | Replace lines, fixtures, and test water flow | Plumber |  | 🕒
HVAC | Clean ducts, replace filters, test system | HVAC Tech |  | 🕒
Interior | Drywall, painting, flooring, cabinets | General Contractor |  | 🕒
Exterior | Roof, siding, gutters, windows | Roofer / Exterior Crew |  | 🕒
Permits & Inspections | Schedule city inspections, get CO | Homeowner / Contractor |  | 🕒
Insurance & Billing | Submit receipts, track supplements | Homeowner / Adjuster |  | 🕒
Contents & Cleaning | Pack-out, clean, restore personal property | Restoration Company |  | 🕒
Fire Prevention | Upgrade alarms, fireproof materials | Homeowner |  | 🕒