## Permit & Inspection Checklist
House Fire Solutions™ – Permit and Inspection Checklist for Fire Rebuilds
Phase / Category | Task / Step | Why It Matters | Who’s Responsible | Status (🕒 / ⚠️ / ✅) | Notes
Pre-Rebuild | Request official fire report | Needed for insurance and permit filings | Homeowner | 🕒
Pre-Rebuild | Site safety clearance (hazards removed) | Confirms safe access and cleanup start | Fire Marshal / Contractor | 🕒
Pre-Rebuild | Verify zoning & land use | Ensures rebuild matches local codes | Planning Dept. | 🕒
Pre-Rebuild | Hire architect/engineer for stamped plans | Required for permits; speeds approvals | Homeowner | 🕒
Pre-Rebuild | Align scope with insurer | Avoids coverage disputes later | Homeowner / Adjuster | 🕒
Permits | Apply: Building Permit | Authorizes structural rebuild | Contractor / Architect | 🕒
Permits | Apply: Demolition Permit | Legal removal of damaged structure | Contractor | 🕒
Permits | Apply: Electrical Permit | Required for panel/wiring work | Licensed Electrician | 🕒
Permits | Apply: Plumbing Permit | Covers water/sewer/gas lines | Plumber | 🕒
Permits | Apply: Mechanical (HVAC) Permit | Covers furnace, ducts, AC | HVAC Contractor | 🕒
Permits | Apply: Roofing Permit | Covers roof replacement/repair | Roofer | 🕒
Permits | Apply: Grading/Tree removal (if needed) | Erosion & site safety compliance | Contractor / Homeowner | 🕒
Pre-Construction | Site safety & debris clearance inspection | Verifies hazards removed | City / Env. Contractor | 🕒
Pre-Construction | Foundation/soil assessment | Confirms stable base for rebuild | Structural Engineer | 🕒
Pre-Construction | Utility disconnect/cap-off | Prevents accidents during demo | Utility Company | 🕒
Pre-Construction | Temporary power pole inspection | Allows power on jobsite | Electrical Inspector | 🕒
Construction | Foundation inspection | Checks footing, slab, anchors | Building Inspector | 🕒
Construction | Framing inspection | Verifies structure, fire blocking | Building Inspector | 🕒
Construction | Rough electrical inspection | Wiring & panel safety before drywall | Electrical Inspector | 🕒
Construction | Rough plumbing inspection | Pressure/vent tests before cover | Plumbing Inspector | 🕒
Construction | Rough HVAC inspection | Ducts, insulation, vents | Mechanical Inspector | 🕒
Construction | Insulation inspection | R-values & vapor barriers | Energy/Building Inspector | 🕒
Construction | Drywall/fire-tape inspection | Fire-rated assemblies verified | Building Inspector | 🕒
Final | Final building inspection | Confirms code & approved plans | Building Inspector | 🕒
Final | Final electrical inspection | GFCIs, power-on test, labeling | Electrical Inspector | 🕒
Final | Final plumbing inspection | Fixtures, drains, pressure | Plumbing Inspector | 🕒
Final | Final HVAC inspection | System performance & safety | Mechanical Inspector | 🕒
Final | Fire safety inspection | Smoke/CO detectors, access | Fire Marshal | 🕒
Final | Certificate of Occupancy (CO) | Home is legally habitable | City/County | 🕒
Post-Rebuild | File approvals & sign-offs | Creates a complete permit record | Contractor / Homeowner | 🕒
Post-Rebuild | Submit docs to insurer | Release recoverable depreciation | Homeowner | 🕒
Post-Rebuild | Update homeowner insurance | Reflects upgraded systems/materials | Homeowner | 🕒
Post-Rebuild | Optional fire prevention inspection | Verifies added safety upgrades | Fire Dept. / Consultant | 🕒

## Permit & Inspection Tracker
House Fire Solutions™ – Permit & Inspection Tracker
Permit / Inspection | Permit # / Ref | Date Applied | Date Approved | Inspector / Dept. | Passed? (Y/N) | Notes
Building Permit |  |  |  | City Building Dept.
Demolition Permit |  |  |  | City Building Dept.
Electrical Rough Inspection |  |  |  | Electrical Inspector
Plumbing Rough Inspection |  |  |  | Plumbing Inspector
HVAC Rough Inspection |  |  |  | Mechanical Inspector
Final Building Inspection |  |  |  | Building Inspector
Certificate of Occupancy |  |  |  | City / County

## Rebuild Progress Log
House Fire Solutions™ – Rebuild Progress Log
Phase | Key Tasks | Responsible Party | Start Date | Completion Date | Inspection Passed? (Y/N) | Comments
Foundation | Excavate, pour footings, set anchors | Contractor
Framing | Walls, headers, fire blocking | Contractor
Rough MEP | Electrical, Plumbing, HVAC rough-ins | Licensed Trades
Insulation | Install to code R-values | Contractor
Drywall/Fire Tape | Hang, tape, and inspect fire-rated assemblies | Contractor
Finals | Electrical, plumbing, HVAC, building final inspections | Inspectors