| Task | Estimated Completion Date |
| --- | --- |

Stage 1:  Housing Committee Decision

| Drawings, drainage strategy and highways design to be worked up (Site Plan, Elevations, Floor Plans, Street Scenes), incorporating highways pre-app comments already received | End March 2026 |
| --- | --- |
| Pre App meeting with Planning + formal response | Late April 2026 |
| Drawings to be revised in line with pre-app response | Mid-May 2026 |
| Meet with Uley Parish Council & Uley Primary School to share site layout (prior to Housing Committee) - feedback to be reported into Housing Committee | Mid-May 2026 |
| Housing Committee report published | 1st June 2026 |
| Housing Committee | 9th June 2026 (NB next Committee date 15th September) |

Stage 2:  Pre Planning Application Submission (subject to Housing Committee Approval to proceed)

| Drawings to be updated (if required) and public consultation information boards created | Mid/Late June 2026 |
| --- | --- |
| Meet with Parish Council & Uley Primary School (prior to public consultation) | Late June 2026 |
| Pre-Planning Public Consultation Drop in Event (start of consultation) | Early- Mid July 2026 |
| Pre-planning Public Consultation Period on-line survey open (4-6 Weeks) | End August 2026 |
| Review of consultation feedback and drawing revision (as required) following public consultation and preparation for planning submission | Mid Oct 2026 |
| Confirm any changes to Parish Council | End October 2026 |
| Planning Submission | End October 2026 |
| Planning consultation open | November 2026 |
| Planning Determination - Average 6 months (This is estimated, could vary significantly) | May 2027 |

Stage 3: Construction Phase (Subject to grant of Planning Permission)

| Start Contractor procurement | June 2027 |
| --- | --- |
| Appoint contractor (assumes within budget) | October 2027 |
| Contractor Mobilisation Period (assume 4 months) | October 2027 to February 2027 |
| Construction (Anticipated 18 months – programme to be confirmed by contractor) | March 2028 – September 2029 |