The Knoll, Uley
Key Milestones
	Task 
	Estimated Completion Date



Stage 1:  Housing Committee Decision

	Drawings, drainage strategy and highways design to be worked up (Site Plan, Elevations, Floor Plans, Street Scenes), incorporating highways pre-app comments already received
	End March 2026

	Pre App meeting with Planning + formal response
	Late April 2026

	Drawings to be revised in line with pre-app response
	Mid-May 2026

	Meet with Uley Parish Council & Uley Primary School to share site layout (prior to Housing Committee) - feedback to be reported into Housing Committee 
	Mid-May 2026

	Housing Committee report published 
	1st June 2026 



	Housing Committee
	9th June 2026
(NB next Committee date 15th September)




Stage 2:  Pre Planning Application Submission (subject to Housing Committee Approval to proceed)

	Drawings to be updated (if required) and information boards created for drop in event. 
	August 2026

	Offer to meet with Parish Council & Uley Primary School (prior to drop in event)
	September 2026

	Information Drop-in Event 
	30th September 2026

	Online Feedback Form Open (3 weeks) 
	30th September – 21st October 

	Review of feedback and drawing revision (as required) and preparation for planning submission
	Mid-End November 2026

	Confirm any changes to Parish Council
	End November 2026

	Planning Submission
	End November 2026

	Planning consultation open
	December 2026

	Planning Determination - Average 6 months (This is estimated, could vary significantly)
	June 2027 




Stage 3: Construction Phase (Subject to grant of Planning Permission)

	Start Contractor procurement
	July 2027

	Appoint contractor (assumes within budget)
	January 2028

	Contractor Mobilisation Period (assume 4 months)
	January 2028 to May 2028 

	Construction (Anticipated 18 months – programme to be confirmed by contractor) 

	June 2028 – December 2029



