| Task | Estimated Completion Date |
| --- | --- |

Stage 1:  Housing Committee Decision

| Drawings, drainage strategy and highways design to be worked up (Site Plan, Elevations, Floor Plans, Street Scenes), incorporating highways pre-app comments already received | End March 2026 |
| --- | --- |
| Pre App meeting with Planning + formal response | Late April 2026 |
| Drawings to be revised in line with pre-app response | Mid-May 2026 |
| Meet with Uley Parish Council & Uley Primary School to share site layout (prior to Housing Committee) - feedback to be reported into Housing Committee | Mid-May 2026 |
| Housing Committee report published | 1st June 2026 |
| Housing Committee | 9th June 2026 (NB next Committee date 15th September) |

Stage 2:  Pre Planning Application Submission (subject to Housing Committee Approval to proceed)

| Drawings to be updated (if required) and information boards created for drop in event. | August 2026 |
| --- | --- |
| Offer to meet with Parish Council & Uley Primary School (prior to drop in event) | September 2026 |
| Information Drop-in Event | 30th September 2026 |
| Online Feedback Form Open (3 weeks) | 30th September – 21st October |
| Review of feedback and drawing revision (as required) and preparation for planning submission | Mid-End November 2026 |
| Confirm any changes to Parish Council | End November 2026 |
| Planning Submission | End November 2026 |
| Planning consultation open | December 2026 |
| Planning Determination - Average 6 months (This is estimated, could vary significantly) | June 2027 |

Stage 3: Construction Phase (Subject to grant of Planning Permission)

| Start Contractor procurement | July 2027 |
| --- | --- |
| Appoint contractor (assumes within budget) | January 2028 |
| Contractor Mobilisation Period (assume 4 months) | January 2028 to May 2028 |
| Construction (Anticipated 18 months – programme to be confirmed by contractor) | June 2028 – December 2029 |