2026 Large Equipment Needed

2 Telehandles-Need them starting June 19 for Electricians and Surveyors

Unload electric trailer and stage for 3-week installation

Most electric inventory is in bins on pallets, so big log chain is needed to hook pallets to the rear of trailer for unloading

Electricians will need them from June 15-July for take down after the show.

Tent vendor will need them from June 27th (tentative) through July 20th (tentative take down)

Unload sign trailer which is also palletized. Some years, signs are sorted in advance with non-necessary signs put back for future years. Radio fleet, flagpole and assorted equipment also in sign trailer.

Trencher-The electricians will need a trencher when they start setting up to bury electrical cables. One that fits on a Bobcat or Skidloader is large enough usually.

Scissors lift-Needed starting June 26

Electrician needs for week prior to hang big tent lighting

Tent company need starting June 27 (tentative) to help erect big tents

Pay Loader

2025 got one from Brooks Tractor (Exhibitor) to help unload/load large exhibitor equipment and to carry large materials. Week prior through egress/take down after the show.

200-300hp Tractor-

Need one large tractor with 8 hydraulic ports to pull large equipment to the customer’s lots and to unfold tillage equipment. It won’t get used much.

Large Skid Loaders

Tram Tractors (13) 12 trams plus drone wagon

Gators/UTV

Garbage pickup

Committee chairs

2-Electricians starting June 15-July take down

Headquarters starting June 22

Escort field demo equipment from show to fields

Golf/Courtesy Carts

4-6 person for “courtesy carts”

2-4 person carts to move VIP’s, media around the grounds

Other equipment

Two wagons with water tank for horses/beef and other livestock on site

Water tank with sprayers to keep dust down on streets

Water tanker with bubblers for attendees? Or other hydration station

Tractor and drag for Equine arena

Extra skidloader buckets for manure storage/pickup for Equine and Beef